## test
num | kind | instruction | reference | Answer | GPT3.5 | details | SMRP支柱定义
1 | Work Management | 1. Best practices are practices that are defined and applied by an organization to improve its operation. These practices may or may not be proven, but results are found to be acceptable. a. True b. False | a, A best practice is a business function, a practice, or a process that is considered superior to all other known methods. It’s a documented strategy and approach used by the most respected, competitive, and profitable organizations. A best practice, when implemented appropriately, should improve performance and efficiency in a specific area. | a | a | Chapter 1. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
2 | Work Management | 2. Maintainability is measured by PM schedule compliance. a. True b. False | b, Maintainability is defined as ease of maintenance; it’s primarily measured by mean time to repair (MTTR). | b | b | Chapter 6. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
3 | Work Management | 3. All maintenance personnel’s time should be covered by work orders. a. True b. False | a, All maintenance personnel’s time should be counted and documented in CMMS to ensure all repair and maintenance costs are accurate and all maintenance personnel’s time is accounted to the right assets. | a | a | Chapters 3 and 4. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
4 | Work Management | 4. Operations and maintenance must work as a team to achieve improved OEE. a. True b. False | a, OEE is calculated as availability × performance × quality. Operations and maintenance both impact this metric and need to work together as a team to achieve higher OEE. | a | a | Chapter 7. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
5 | Work Management | 5. A best practice is to have 90% or more of all maintenance work planned. a. True b. False | a, It is a good practice to plan 90% or more of work. Planned work costs two to three times less than reactive work. | a | a | Chapter 4. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
6 | Strategy Development & Management | 6. 100% of PM and PdM tasks should be developed using FMEA/RCM methodology, at least for critical assets. a. True b. False | a, All PM/PdM tasks should be developed using FMEA/RCM methodology. This ensures cost-effective and correct tasks to mitigate certain risks and to find potential failures before they fail. | a | a | Chapters 3 and 8. | Around the development and management of maintenance strategies
7 | Work Management | 7. Utilization of assets in a world-class facility should be above 85%. a. True b. False | a, Assets cost money to procure, operate, and maintain. They should be utilized 85% or better to get high ROI. Of course, M&R tasks have to ensure their availability. | a | a | Chapters 7 and 9. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
8 | Workforce Management &Leadership | 8. 100% of maintenance personnel’s (craft/technician) time should be scheduled. a. True b. False | a, One hundred percent of maintenance personnel, specifically craft/technician available hours, should be scheduled. Scheduling compliance analysis should provide opportunity to reduce/eliminate waste and improve productivity. | a | b | Chapter 4. | Around managing the workforce and programs to support and contribute to business results
9 | Work Management | 9. Time-based PMs should be about 30% of all PMs. a. True b. False | a, It is a good and cost-effective practice to do more run-/cycle based and condition-based PM. It is also good practice to have calendar-based PMs 30% or less. | a | b | Chapters 3, 4, and 8. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
10 | Work Management | 10. The 10% rule of PM should be applied on critical assets. a. True b. False | a, This rule implies that time-based PM must be accomplished within 10% of the time frequency, or it is out of compliance. It means a quarterly (90 days) PM must be done within ± 9 days of the due date. | a | b | Chapters 3, 4, and 8. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
11 | Work Management | 11. Most emergency work orders should be written by production/operations. a. True b. False | a, Most emergency work orders should be written by production/operations. Operators are with assets all the time, and they should know what needs to be fixed to meet the production schedule. | a | a | Chapters 4 and 7. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
12 | Work Management | 12. It is a common practice for operators to perform PMs. a. True b. False | a, This is true assuming the organization is deploying TPM as one of the best practices. Under TPM philosophy, operators do perform PMs and support maintenance. | a | a | Chapter 7. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
13 | Work Management | 13. The P-F interval can be applied to visual inspections. a. True b. False | a, The primary objective of an inspection is to detect a fault, or to find the start of one, and to correct it before it fails. Faults can be detected visually, or they can be detected by using predictive technologies. | a | a | Chapter 8. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
14 | Work Management | 14. Understanding of a P-F interval should help in optimizing PM frequency. a. True b. False | a, The primary objective is to detect a fault, or to find the start of one, and to correct it before it fails. The PM frequency should be less than the P-F interval. | a | a | Chapter 8. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
15 | Equipment Reliability | 15. The best method of measuring the reliability of an asset is by counting downtime events. a. True b. False | a, Reliability is measured by MTBF, which is operating time divided by the number of failures, or downtime events. Our objective is to reduce downtime events, which will improve MTBF. | a | b | Chapter 6. | About particular metrics, such as for reliability, availability and maintainability
16 | Work Management | 16. The primary purpose of scheduling is to coordinate maintenance jobs for the greatest utilization of the maintenance resources. a. True b. False | a, The goal is to get all work completed as scheduled to minimize waiting time (waste). | a | a | Chapter 4. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
17 | Work Management | 17. What percentage of your assets should be ranked critical based on the risk to business? a. Less than 30% b. 30–50% c. Over 50% | a, We need to take care of (maintain) all the assets. However, we do not have unlimited resources to do that. We need to do everything possible to ensure that all critical assets are being maintained adequately before we get to other or noncritical assets. | a | a | Chapters 3 and 4. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
18 | PHM Technologies | 18. Vibration monitoring can detect uniform impeller wear. a. True b. False | b, Uniform wear will not create any unbalance, hence no vibration. | b | b | Chapter 8. | Related to specific condition assessment technologies
19 | Work Management | 19. Understanding the known and likely causes of failures can help design a maintenance strategy for an asset to prevent or predict failure. a. True b. False | a, If we understand the failure mechanism—how a part or component can fail—we can develop a mitigating maintenance strategy to prevent failure. | a | a | Chapters 6, 8,and 11. | Around the development and management of maintenance strategies
20 | Equipment Reliability | 20. Reliability can be improved easily after a maintenance plan has been put into operation. a. True b. False | b, Reliability is a design attribute. It means that reliability is based on how an asset is designed and with what type of components and their configurations. A maintenance plan cannot change the basic (inherent) reliability unless the components are changed or redesigned. | b | b | Chapters 6 and 8. | About particular metrics, such as for reliability, availability and maintainability
21 | Storeroom & Inventory Management | 21. What percentage of maintenance work should be proactive?a. 100% b. 85% or more c. 50% | b, The proactive work is defined as all work minus unscheduled/ unplanned work. We know that planned and scheduled work will cost less than unscheduled, reactive work. We have found that it is a good practice to have proactive work at 85% or more. | b | c | Chapters 3 and 4. | Work Management
22 | Work Management | 22. MTBF is measured by operating time divided by the number of failures of an asset. a. True b. False | a, MTBF (mean time between failures) is calculated by dividing operating time by the number of failures, or downtime events. | a | a | Chapter 6. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
23 | Equipment Reliability | 23. Maintenance cost will decrease as reliability increases. a. True b. False | a, Initially, when we start an M&R improvement initiative, maintenance cost may go up, but eventually it should come down as the reliability of assets increases. | a | a | Chapters 3 and 6. | About particular metrics, such as for reliability, availability and maintainability
24 | Strategy Development & Management | 24. The “F” on the P-F interval indicates that equipment is still functioning.a. True b. False | b, In the P-F interval curve, F stands for failure, and P stand for potential failure. | b | c | Chapters 6 and 8. | Around the development and management of maintenance strategies
25 | PHM Technologies | 25. A rule of thumb is that on average an experienced planner can plan work for how many craftspeople? a. 10 b. 15 c. 20 or more | b, On average, an experienced planner should be able to plan work for about 15 ± 5 craftspeople, depending upon the type of work. Generally, 15 is a good number. | b | a | Chapter 4. | Related to specific condition assessment technologies
26 | Work Management | 26. Which of the following is not a primary objective for implementing a planning process? a. Reduce reactive work b. Prevent delays during the maintenance process c. Mesh the production schedule and the maintenance schedule | c, It is not a planning function (or a planner’s job) to mesh maintenance and production schedules. However, people may use production schedules to improve their schedule or to identify conflicts. | c | b | Chapter 4. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
27 | Work Management | 27. The best method of measuring the reliability of an asset is to know: a. MTTR b. MTBF c. Both | b, Reliability is measured by MTBF, which is the operating time divided by the number of failures. MTTR is a measure of maintainability. | b | d | Chapters 6 and 9. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
28 | Work Management | 28. With the exception of emergency work orders planning and scheduling will benefit all maintenance work. a. True b. False | a, P&S should benefit all maintenance work. Planned and scheduled work costs much less, and work gets accomplished in a timely manner. | a | c | Chapter 4. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
29 | Equipment Reliability | 29. Leading KPIs predict results. a. True b. False | a, The leading indicators are process indicators, and they lead to the results. For example, PM compliance and backlog are leading indicators. | a | a | Chapter 9. | About particular metrics, such as for reliability, availability and maintainability
30 | Work Management | 30. The sixth S in the 6S (also called 5S plus) process stands for safety. a. True b. False | a, The original 5S (sort, set in order, shine, standardize, and sustain) is a systematic process for improving productivity, quality,and housekeeping. Lately, a sixth S has been added to focus on safety. | a | c | Chapter 7. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
31 | PHM Technologies | 31. RCM stands for: a. Regimented centers of maintenance b. Reliability-centered maintenance c. Reliable centers of maintenance (uses best practices) | b, RCM stands for reliability-centered maintenance. | b | a | Chapter 8. | Related to specific condition assessment technologies
32 | Work Management | 32. The objective of RCM is to preserve functions. a. True b. False | a, The objective of RCM is to preserve function and optimize maintenance needs. | a | c | Chapter 8. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
33 | Work Management | 33. It does not cost anything to keep a part (material) in the storeroom after we bought and paid for it. a. True b. False | b, It costs money, about 20–25% of the value of the part (material),to stock in the storeroom. The storeroom needs to be maintained and managed, and that costs money. | b | a | Chapter 5. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
34 | Work Management | 34. The inventory turnover ratio for an MRO store should be: a. Less than 2 b. Between 4 and 6 c. Over 6 | a, It should be less than 2 for maintenance-related spares. The long lead items and “A”-type inventory are expensive to keep but needed for catastrophic failures. | a | d | Chapter 5. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
35 | Work Management | 35. PM compliance is a lagging KPI. a. True b. False | b, Lagging indicators are the results. Leading indicators are process indicators, and they lead to the results. For example, as noted earlier, PM compliance and backlog are leading indicators. | b | b | Chapter 9. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
36 | Work Management | 36. Reliability is one key component of OEE. a. True b. False | b, Reliability is not a component of OEE; OEE = availability × performance × quality. | b | b | Chapter 7. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
37 | PHM Technologies | 37. Reliability and maintainability can only be designed in. a. True b. False | a, Reliability and maintainability are design attributes. An asset’s performance depends upon how it is designed for reliability and maintainability.A maintenance strategy cannot change the basic (inherent)reliability. However, training the workforce in repair techniques and providing the right tools willimprove the asset availability. | a | d | Chapter 6. | Related to specific condition assessment technologies
38 | Work Management | 38. Creating a reliability culture from a reactive mode can be accomplished in a short period of time if enough resources are made available. a. True b. False | b, Changing culture takes a long time. We cannot change a sustainable culture overnight. It is a journey that takes many years and is not dependent on resources; it is time. | b | b | Chapter 2. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
39 | Work Management | 39. Karl Fischer’s coulometric titration method is an effective technique to determine the metallic content (in PPM) in an oil sample. a. True b. False | b, Karl Fischer’s method is used for determining water content (in PPM) in an oil sample. | b | b | Chapter 8. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
40 | Equipment Reliability | 40. An IR thermography window is an effective method to satisfy NFPA 70E arc flash requirements. a. True b. False | a, IR thermography windows with an IR camera are being used effectively to detect any hot spots or potential problems in electrical cabinets, switchgears, etc., safely to help in meeting NFPA 70E arc flash requirements. | a | c | Chapters 8 and 12. | About particular metrics, such as for reliability, availability and maintainability
41 | Work Management | 41. FMEA is applicable only to assets currently in use. a. True b. False | b, FMEA can be used for any asset, whether in use or not. In fact, it is a good practice to apply to new systems being designed/developed to identify potential failure modes. | b | c | Chapters 8 and 11. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
42 | Strategy Development & Management | 42. RCM methodology can’t be used effectively on new systems being designed. a. True b. False | b, RCM can be used on new or “in-use” systems. In fact, it is a good application for a new system under development to use RCM methodology to identify potential failure modes and to develop an effective PM plan. | b | b | Chapter 8. | Around the development and management of maintenance strategies
43 | PHM Technologies | 43. Properly training the M&R workforce can increase asset and plant (factory) availability. a. True b. False | a, Training the M&R workforce in the application of new tools/techniques will reduce repair time, resulting in higher availability. | a | b | Chapters 10 and 11. | Related to specific condition assessment technologies
44 | Work Management | 44. TPM is a type of maintenance performed by the operators. a. True b. False | a, Total productive maintenance (TPM) is another maintenance strategy where an operator does some maintenance, sometimes called first level, e.g., changing filters, making minor adjustments, etc., and becomes part of the maintenance crew in supporting major repairs. | a | c | Chapter 7. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
45 | PHM Technologies | 45. Lagging KPIs are the results of a process. a. True b. False | a, Lagging indicators are the results. For example, maintenance cost and availability are lagging indicators. | a | b | Chapter 9. | Related to specific condition assessment technologies
46 | Work Management | 46. EOQ improves the inventory turn ratio. a. True b. False | b, EOQ (economic order quantity) calculates the optimum order quantity to optimize inventory cost. It does not impact the inventory turnover ratio. | b | a | Chapter 5. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
47 | Work Management | 47. New incoming oil from the supplier is always clean and ready to be used. a. True b. False | b, It has been found that the incoming oil is not usually clean and does not meet cleanliness requirements. Most organizations establish an oil cleaning system to check and clean all incoming oil to ensure that the new oil meets cleanliness requirements. | b | a | Chapter 8. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
48 | Work Management | 48. Which phase of the asset life cycle has the highest cost? a. Design b. Acquisition c. O&M | c, The O&M phase usually has the highest cost in an asset’s life cycle. | c | b | Chapter 6. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
49 | Work Management | 49. Most of the maintenance costs become fixed: a. After installation of the asset b. During the operation phase c. During the design phase | c, Most maintenance costs get fixed during the design phase. | c | b | Chapter 6. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
50 | Work Management | 50. RCM provides the best results when used: a. During operation (production) b. During design/development c. After an asset has failed or keeps failing d. During build/fabrication | b, RCM should be used in the design phase to get maximum benefits. | b | c | Chapters 6 and 8. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
51 | Work Management | 51. How soon we can restore an asset is measured by:a. MTBF b. MTTR c. MTBMA d. None of the above | b, MTTR is a measure of how soon we can bring the asset back to operations. | b | b | Chapter 6. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
52 | Work Management | 52. Availability is a function of: a. MTBF b. MTTR c. Uptime d. Uptime and downtime | d, Availability is calculated by uptime divided by uptime plus downtime. | d | c | Chapter 6. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
53 | Work Management | 53. The failure rate of a component/asset can be calculated by knowing: a. The number of failures b. MTBF c. MTTR d. Uptime | b, Failure rate is the inverse of MTBF. | b | a | Chapter 6. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
54 | Work Management | 54. The biggest benefit of a failure mode and effects analysis occurs during: a. The operation phase b. The maintenance phase c. The design phase d. None of the above | c, FMEA should be performed during the design phase to identify failure modes; those modes could be eliminated or their impact reduced or mitigated cost-effectively. | c | c | Chapters 6 and 11. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
55 | Work Management | 55. PM schedule compliance should be equal to or greater than 95%. a. True b. False | a, High PM schedule compliance (95% or better) will catch potential failures before they happen, thereby reducing the unexpected breakdowns. | a | b | Chapters 3 and 4. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
56 | Work Management | 56. Maintainability is measured by: a. The PM schedule compliance rate b. The average time between maintenance actions c. The percentage of time that equipment is working satisfactorily d. The average time required to restore the equipment | d, Maintainability is ease of maintenance and is measured by how quickly the equipment/asset can be put back to operation. | d | b | Chapters 3 and 6. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
57 | Work Management | 57. Which process ensures that resources material and equipment are available before a job is performed? a. Planning b. Scheduling c. Inventory | b, The key function of the scheduling process is to ensure all resources required, including permits, are available before the job is scheduled to be performed. | b | a | Chapters 3 and 4. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
58 | Strategy Development & Management | 58. Which analysis identifies a cost-effective approach to reduce maintenance and operational problems? a. Weibull b. FTA c. Pareto d. Bottleneck | c, Pareto analysis identifies what few vital assets need to be taken care of first to get maximum benefit. | c | b | Chapter 11. | Around the development and management of maintenance strategies
59 | Work Management | 59. When a task/job is completed who should close out the work order in a CMMS system? a. Person who did the work b. Supervisor c. Planner d. Scheduler | a, The technician who did the work is the best person to fill all the required information to close out the work order. However, it is suggested that the supervisor should review the work order to ensure the information is correct before the work order gets closed out. | a | a | Chapters 3 and 4. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
60 | PHM Technologies | 60. The objective of an agreement between operations and maintenance is to: a. Clarify who is responsible when a problem arises b. Minimize confusion c. Clarify roles and responsibilities d. All of the above | d, The agreement between operations and maintenance is a good practice to ensure that there is no conflict or confusion when a problem arises about who is responsible and when the repair will start. | d | b | Chapters 3 , 4 , and 7 . | Related to specific condition assessment technologies
61 | Work Management | 61. Which work order characteristic (element) is most important? a. Description of work completed b. Cost of work c. Asset ID d. Cost/charge number | c, The asset ID is the key element (field) on a work order to ensure that work-related information is going to the right asset. | c | b | Chapters 3 and 4. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
62 | Work Management | 62. Which factor is most influential in developing the skills of the M&R team members? a. Current maintenance repair skills b. Current plant performance requirements c. Future plant performance requirements d. None of the above | c, The needs of the future (the next few months, 1–3 years, etc.) plant should determine what assets and skills will be required to perform M&R tasks effectively. | c | c | Chapter 10. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
63 | Work Management | 63. The first stage of team development is known as:a. Norming b. Forming c. Storming d. Warming | b, The team development goes through four stages: forming, storming, norming, and performing. | b | b | Chapter 10. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
64 | Equipment Reliability | 64. Which maintenance strategy has a goal of zero defects zero breakdowns and an effective workplace design? a. CM b. TPM c. RTF | b, Total productive maintenance (TPM) has the goal of zero defects, safe workplace, etc. | b | c | Chapter 7. | About particular metrics, such as for reliability, availability and maintainability
65 | Work Management | 65. A mission statement is a statement of an organization’s: a. Structure b. Roles and responsibilities c. Purpose—what the organization wants to do d. Net worth | c, The mission statement should tell us about the organization’s purpose and what the organization does and how it does it. | c | c | Chapter 2 . | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
66 | PHM Technologies | 66. In which phase of the asset’s life cycle is the highest cost incurred? a. Design and procure b. Build and install c. Operate and maintain d. Decommission and dispose | c, The operate and maintain phase, also known as the value creation phase of the asset, has the highest life cycle cost, about 70–80%. | c | b | Chapter 6. | Related to specific condition assessment technologies
67 | Work Management | 67. Optimizing inventory levels by ordering the right quantity at a specific time interval in order to minimize inventory cost but still meet customer needs is called: a. Inventory cost analysis b. Economy order quantity c. Inventory turns analysis | b, Economic order quantity (EOQ) is a technique to optimize inventory levels by ordering the right quantity at a specific time to minimize inventory cost. | b | b | Chapter 5. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
68 | PHM Technologies | 68. Who is a stakeholder? a. A person responsible for preparing the project budget b. A person or organization that can affect be affected by or believe to be affected by a decision or activity c. A person or organization that performs/supports change management to make a new improvement project succeed | b, Also known as an interested party. | b | b | Chapter 2. | Related to specific condition assessment technologies
69 | Work Management | 69. The last step in a basic communication model is to: a. Decode b. Encode c. Provide feedback/responsed. Transmit a message | c, Feedback is what the receiver sends back to the sender. This is to ensure that the receiver got the right (intended) message. | c | c | Chapter 10. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
70 | Strategy Development & Management | 70. RPN (risk priority number) is the: a. Sum of severity (S) occurrence (O) and detection (D) b. Product of severity (S) occurrence (O) | b, The RPN is a mathematical product of numerical severity S, occurrence O, and detection D. | b | a | Chapter 11 . | Around the development and management of maintenance strategies
71 | PHM Technologies | 71. What does a change agent do? a. Supports change b. Initiates change c. Opposes changed. Helps implement change | d, A change agent helps (supports) in the adoption/implementation of a cause, policy, or project. | d | c | Chapter 2. | Related to specific condition assessment technologies
72 | Work Management | 72. Which of the following is a reliability tactic? a. Implementing a preventive maintenance program b. Improving individual components to increase MTBF c. Training technicians to improve repair time and reduce MTTR d. Optimizing PM to reduce maintenance costs | b, The MTBF of a component/asset can be increased by redesigning the component/asset or by replacing it with a high-reliability part. | b | c | Chapter 6. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
73 | Work Management | 73. TPM (total productive maintenance) has the potential of providing almost a seamless integration between: a. Production and quality b. Maintenance and quality c. Production and maintenance d. Production and engineering | c, TPM is a team approach where production and maintenance work together to ensure assets operate safely with minimum breakdowns. | c | c | Chapter 7. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
74 | Work Management | 74. The process that is intended to find potential failures and repair or replace bad components before they fail is known as: a. Preventive maintenance b. Failure-finding maintenance c. Troubleshooting maintenance d. Breakdown maintenance | a, The objective of preventive maintenance inspection and servicing at specified intervals is to find problems and fix them before they fail. | a | a | Chapters 3 , 4 , and 8. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
75 | Work Management | 75. A maintenance engineer has a list of pump failure modes and frequency of occurrence. Which of the following diagrams can help to prioritize maintenance tasks? a. Ishikawa diagram b. Bathtub curve c. Pareto chart d. Reliability growth diagram | c, Pareto chart analysis identifies which few vital items (failures) need to be corrected first to get maximum benefit. | c | c | Chapter 11 . | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work
76 | Work Management | 76. A fault tree analysis (FTA) typically generates a a. Set of statistical data b. Report on the relative costs of design options c. Diagram showing a hierarchy of failure causesd. List for a specific plan of action | c, The FTA tool starts with the final failure or event and progressively traces each cause that led to the previous cause. | c | c | Chapter 11. | Work Management Related to Work Planning, Scheduling and Execution as well as different types of work